## Exhibit A
Exhibit A: FY 2016/2017 South Bay Highway Program Metro Budget Request
|  | Updated: 10/20/15 |  |  |  | 2016-2017 (FY 17) |  |  |  |  | 2017-2018 (FY 18) |  |  |  | Future Years | 2018-2019 (FY 19) |  |  |  |  | 2019-2020 (FY 20) |  |  |  |  | 2020-2021 (FY 21) |  |  |  |  | 2021-2022 (FY 22) |  |  |  |  | Total Project Est. Cost |  | Eligibility and Matching Policy
Metro Project ID FA Type | Phase | Lead Agency / Description | Phase Cost | Measure R Share | Est. Reimburse. by 6/30/16 | Q1 16-17 July-Sept | Q2 16-17 Oct-Dec | Q3 16-17 Jan-March | Q4 16-17 April-June | 16-17 TOTAL | Q1 17-18 July-Sept | Q2 17-18 Oct-Dec | Q3 17-18 Jan-March | Q4 17-18 April-June | 17-18 TOTAL | Q1 18-19 July-Sept | Q2 18-19 Oct-Dec | Q3 18-19 Jan-March | Q4 18-19 April-June | 18-19 TOTAL | Q1 19-20 July-Sept | Q2 19-20 Oct-Dec | Q3 19-20 Jan-March | Q4 19-20 April-June | 19-20 TOTAL | Q1 20-21 July-Sept | Q2 20-21 Oct-Dec | Q3 20-21 Jan-March | Q4 20-21 April-June | 20-21 TOTAL | Q1 21-22 July-Sept | Q2 21-22 Oct-Dec | Q3 21-22 Jan-March | Q4 21-22 April-June | 21-22 TOTAL | Total Project Est. Cost (All Phases and Sources) | Total Cost Est. Source | Eligibility | Measure R Percent | Measure R Revised by Lead Agency? | MBR Measure R Share
ADMINISTRATIVE
Administration & Miscellaneous Expense |  |  | 1022958.68 | 1022958.68 | 840930.68 | 7035 | 7035 | 7035 | 7035 | 28140 | 7247 | 7247 | 7247 | 7247 | 28988 | 7463 | 7463 | 7463 | 7463 | 29852 | 7688 | 7688 | 7688 | 7688 | 30752 | 7918 | 7918 | 7918 | 7918 | 31672 | 8156 | 8156 | 8156 | 8156 | 32624 |  |  |  | 100% |  | 100%
Program Development and Misc. Expenses (development, oversight, and intergovernmental relations) |  |  | 5696599.02 | 5696599.02 | 2439624.02 | 129595 | 129596 | 129597 | 129597 | 518385 | 140134 | 140134 | 140134 | 140134 | 560536 | 121975 | 121977 | 121977 | 121977 | 487906 | 136371 | 136372 | 136373 | 136373 | 545489 | 130825 | 130827 | 130827 | 130827 | 523306 | 155337 | 155338 | 155339 | 155339 | 621353 | 17577216.09 | All Admin |  | 100% |  | 100%
Feasibility Studies (previous reimbursement) |  |  | 1696661.39 | 1696661.39 | 496661.39 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 400000 |  |  |  |  | 400000 |  |  |  |  | 400000 | [5 empty] | 100%
ACTIVE FEASIBLITY/PLANNING STUDIES
EXECUTED MR312.57 PD | Feasibility Study | City of El Segundo Park Place from Nash St. to Allied Way, Roadway extension and railroad grade separation | 350000 | 350000 | 150000 |  | 150000 |  |  | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 35850000 | From Lead Agency |  | 50% | Future Funding Mix Not Identified | 100%
EXECUTED FEAS STUDY SBHP TO 2015-1 | Feasibility Study | Port of LA Vincent Thomas Bridge (SR-47) I-110 Connector | 1000000 | 1000000 | 112000 | 290000 | 314000 | 234000 | 50000 | 888000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1000000 | Construction Separate |  | 100% EA |  | 100%
EXECUTED MR312.24 | PA/ED | Caltrans PAED I-110 Auxiliary lane from SR-91 to Torrance Blvd Auxiliary lane & 405/110 Connector | 1500000 | 1500000 | 1500000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 30000000 | Placeholder Est. |  | 50% | Future Funding Mix Not Identified | 100%
EXECUTED MR312.25 | PA/ED | Caltrans PAED I-405 at 182nd St./Crenshaw Boulevard | 1700000 | 1700000 | 1700000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 34000000 | Placeholder Est. |  | 50% | Future Funding Mix Not Identified | 100%
EXECUTED MR312.56 | PA/ED | City of Los Angeles Review of Feas. Study on Del Amo Blvd from Western Ave to Vermont Ave. | 100000 | 100000 | 3277 | 24180.75 | 24180.75 | 24180.75 | 24180.75 | 96723 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3000000 | Placeholder Est. |  | 80% | Future Funding Mix Not Identified | 100%
EXECUTED MR312.16 | PA/ED | Los Angeles County Del Amo Boulevard from Normandie Boulevard to Vermont Ave | 1900000 | 1900000 | 1900000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 26000000 | Placeholder Est. |  | 50% | Future Funding Mix Not Identified | 100%
COMMITTED FEASIBLITY/PLANNING STUDIES
COMMITTED MR312.30 | Feasibility Study | Caltrans I-405 from I-110 to I-105 and I-105 from I-405 to Crenshaw: Corridor Refinement Studies | 700000 | 700000 |  | 75000 | 75000 | 75000 | 75000 | 300000 | 100000 | 100000 | 100000 | 100000 | 400000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 14000000 | Placeholder Est. |  | 100% EA | Future Funding Mix Not Identified | 100%
COMMITTED MR312.45 | PA/ED | Caltrans PAED/Implement an Integrated Corridor Management System along the SR -110 Corridor between Artesia Boulevard and the I-405. The project will integrate freeway, arterial and transit operations, implement a Decision Support System for coordinated agency operations and traveler information systems. | 1000000 | 1000000 | [5 empty] | 0 |  |  |  |  | 0 | 125000 | 125000 | 125000 | 125000 | 500000 | 125000 | 125000 | 125000 | 125000 | 500000 |  |  |  |  | 0 |  |  |  |  | 0 | 20000000 | Placeholder Est. |  | 100% EA | Future Funding Mix Not Identified | 100%
COMMITTED SBHP TO 2014-1 | Feasibility Study | City of El Segundo Aviation Blvd, Douglas St. and El Segundo Blvd. Commuter Bikeways Study | 150000 | 150000 |  |  | 150000 |  |  | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3000000 | Placeholder Est. |  | 100% EA | Future Funding Mix Not Identified | 100%
COMMITTED FEAS STUDY SBHP TO #-# | Feasibility Study | City of Torrance Pacific Coast Highway (SR-1) / Hawthorne Blvd. (SR-107) Park & Ride Feasibility Study | 150000 | 150000 | [5 empty] | 0 | 150000 |  |  |  | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3000000 | Placeholder Est. |  | 100% EA | Future Funding Mix Not Identified | 100%
COMMITTED FEAS STUDY SBHP TO #-# | Feasibility Study | City of Torrance 182nd St from Kingsdale Ave to Harbor Gateway Transit Center (e/o Vermont Ave.): feasibility of study various corridor improvements (intersection improvements, ITS, bicycle facilities, etc.). | 300000 | 300000 |  |  |  | 300000 |  | 300000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 6000000 | Placeholder Est. |  | 100% EA | Future Funding Mix Not Identified | 100%
NEW REQUEST FOR FEASIBILITY/PLANNING STUDIES
Requested | Feasibility Study | Caltrans I-405 from I-110 to I-105 (including a mile on either side of the freeway): Identify and prioritize operational improvements (aux. lanes, interchange configuration) to reduce travel delay. | 700000 | 700000 |  | 50000 | 50000 | 75000 | 75000 | 250000 | 75000 | 75000 | 75000 | 75000 | 300000 | 75000 | 75000 |  |  | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 14000000 | Placeholder Est. | Eligible | 100% |  | 100%
Requested | PSR | Caltrans SR-1 from eastern boundary of Carson to eastern boundary of Torrance - PSR | 170000 | 170000 |  |  |  | 85000 | 85000 | 170000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3400000 | Placeholder Est. | Eligible | 100% |  | 100%
Requested | PSR | Caltrans Western Ave.(SR-213) from Palos Verdes Drive North to northern boundary of Gardena - PSR | 170000 | 170000 |  |  |  | 85000 | 85000 | 170000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3400000 | Placeholder Est. | Eligible | 100% |  | 100%
Requested | Feasibility Study | City of Carson Avalon Boulevard Bridge over the Dominguez Channel: Investigate feasibility of an additional lane on the west side for a bike lane and widening of the east side sidewalk to improve flow in a constrained location. | 60000 | 60000 | [5 empty] | 0 | 60000 |  |  |  | 60000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 5000000 | Placeholder Est. | Eligible | 100% |  | 100%
Requested | PA/ED | City of El Segundo PA/ED Park Place from Nash St to Allied Way- Roadway extension and railroad grade separation, including utility and railroad relocation and construction. | TBD | TBD |  |  |  | 1000000 |  | 1000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | - | Design/Const Separate | Eligible - Nexus Project |  |  | 100%
Requested | PA/ED + Est Const./ ROW funding | City of Hermosa Beach PA/ED Aviation Bl from PCH to Prospect Ave - Arterial Improvements. | $1,800,000 PA/ED, $42m Cost/ROW | 22300000 |  |  |  | 1800000 |  | 1800000 |  |  |  |  | 0 | 273000 | 273000 | 894000 | 894000 | 2334000 | 894000 | 894000 |  | 1820000 | 3608000 | 1820000 | 1820000 | 1820000 | 1820000 | 7280000 | 1820000 | 1820000 | 1819000 | 1819000 | 7278000 | 44599000 | From Lead Agency | Eligible with Nexus Project elements | 100% | Yes | 50%
Requested | PA/ED | City of Inglewood PA/ED for Florence Ave at La Brea Ave - Construct new Downtown Inglewood Transit Center at La Brea Station of Crenshaw Line | 1500000 | 1500000 |  | 30000 | 30000 | 30000 | 30000 | 120000 | 30000 | 213750 | 213750 | 213750 | 671250 | 213750 | 213750 | 213750 | 67500 | 708750 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1500000 | Total Cost | Eligible, bus turnouts and demand reduction | 100% |  | 100%
Requested | PA/ED | Port of LA PA/ED for SR-47/Vincent Thomas Bridge and Front St/Harbor Bl Interchange Reconfiguration. | 11726000 | 11726000 | [5 empty] | 0 | 88125 | 88125 | 88125 | 88125 | 0 | 187500 | 187500 | 187500 | 187500 | 750000 | 187500 | 187500 | 187500 | 187500 | 750000 | 1281250 | 1281250 | 1281250 | 1281250 | 5125000 | 1275250 | 1275250 | 1275250 | 1275250 | 5101000 | 23452000 | From Lead Agency | Eligible | 50% | Yes | 50%
Requested | Feasibility Study | City of Rancho Palos Verdes Western Ave (SR-213) from Palos Verdes Drive North to 25th St,: Feasibility study for improvements in coordination with Lomita, LADOT, and Caltrans. | 90000 | 90000 |  | 25000 | 15000 | 30000 | 20000 | 90000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1800000 | Placeholder Est. | Eligible | 100% |  | 100%
ACTIVE PROJECTS
EXECUTED MR312.11 | Design/ Construction | Caltrans ITS: I-405, I-110, I-105, SR-91 at freeways ramp/arterial signalized intersections - DCCM | 5000000 | 5000000 | 5000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 25000000 | Placeholder Est. |  | 100% EA |  | 100%
EXECUTED MR312.29 | Design/ Construction | Caltrans Pacific Coast Highway (SR-1) ITS with parallel arterials from I-105 to I-110 | 9000000 | 9000000 | 5472000 | 1250000 | 850000 | 728000 | 700000 | 3528000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 9000000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.37 | Design/ Construction | City of Carson Sepulveda Boulevard widening from Alameda Street to ICTF Driveway | 1158000 | 1158000 | 1158000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1158000 | Total Cost |  | 100% |  | 100%
EXECUTED MR312.17 | Design/ Construction | City of Gardena Rosecrans Ave Arterial Improvements From Vermont Ave to Crenshaw Blvd. | 5140000 | 5140000 | 1907759 | 808060.25 | 808060.25 | 808060.25 | 808060.25 | 3232241 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 5140000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.33 | Design/ Construction | City of Hawthorne Aviation Bl at Marine Ave; construct westbound right-turn lane. | 3600000 | 3600000 | 155000 | 145000 | 125000 | 25000 | 50000 | 345000 | 15000 | 30000 | 25000 | 230000 | 300000 |  |  | 300000 | 1500000 | 1800000 | 1000000 |  |  |  | 1000000 |  |  |  |  | 0 |  |  |  |  | 0 | 3600000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.05 | Design/ Construction | City of Hermosa Beach Pacific Coast Highway (SR-1) between Anita St and Artesia Blvd: Improvements | 304000 | 304000 | 202936 | 101063 |  |  |  | 101063 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 304000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.12 | Design/ Construction | City of Inglewood Citywide ITS Phase IV | 3500000 | 3500000 | 3500000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3500000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.15 | Design/ Construction | City of Lawndale Inglewood Ave From 156th st to I-405 SB On Ramp Improvements | 500000 | 500000 | 500000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 500000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.36 | Construction | City of Lawndale Traffic Signal Improvements Citywide | 1500000 | 1500000 | 1500000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1500000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.43 | Design/ Construction | City of Lomita Intersection Improvements at Western (SR-213) /Palos Verdes Dr. & Pacific Coast Highway (SR-1)/Walnut | 900000 | 900000 | 800000 | 100000 |  |  |  | 100000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 900000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.28 | Construction | City of Manhattan Beach Seismic retrofit of Sepulveda Blvd (SR-1) bridge 53-62 | 9100000 | 9100000 | 6461664 | 1319168 | 1319168 |  |  | 2638336 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 9100000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.04 | Construction | City of Manhattan Beach Sepulveda Blvd at Marine Ave (WB Left Turn Lane) | 365000 | 365000 | 364500 | 500 |  |  |  | 500 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 365000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.06 | Design/ Construction | City of Redondo Beach Pacific Coast Highway (SR-1) Arterial Improvements from Anita St to Palos Verdes Blvd | 1400000 | 1400000 | 150000 | 75000 | 115000 | 30000 | 280000 | 500000 | 250000 | 250000 | 250000 |  | 750000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1400000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.07 | Construction | City of Redondo Beach Pacific Coast Highway (SR-1) at Torrance Blvd Intersection Improvements | 585000 | 585000 | 127000 | 10000 | 148000 | 150000 | 150000 | 458000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 585000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.08 | Design/ Construction | City of Redondo Beach Pacific Coast Highway (SR-1) at Palos Verdes Blvd Intersection Improvements | 320000 | 320000 | 320000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 320000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.20 | Design/ Construction | City of Redondo Beach Aviation Blvd at Artesia Blvd Intersection Improvements | 847000 | 847000 | 350000 | 165000 | 172000 | 160000 |  | 497000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 847000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.42 | Design/ Construction | City of Redondo Beach Inglewood Ave at Manhattan Beach Bl: Add SB right-turn lane south of railroad tracks to Manhattan Beach Bl | 5175000 | 5175000 | 117000 | 70000 | 68000 | 733000 | 782000 | 1653000 | 730000 | 730000 | 40000 | 40000 | 1540000 | 10000 | 365000 | 375000 | 375000 | 1125000 | 370000 | 370000 |  |  | 740000 |  |  |  |  | 0 |  |  |  |  | 0 | 5175000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.10 | Design/ Construction | City of Torrance Pacific Coast Highway (SR-1) at Hawthorne Blvd (SR-107) Intersection Improvements | 19600000 | 19600000 | 9600000 | 500000 | 500000 | 500000 | 8500000 | 10000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 19600000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.23 | Design/ Construction | City of Torrance Torrance Park and Ride Regional Terminal | 18100000 | 18100000 | 10000000 | 3000000 | 3000000 | 2100000 |  | 8100000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 18100000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.26 | Design/ Construction | City of Torrance I-405 at 182nd St. /Crenshaw Blvd. operational improvements | 15300000 | 15300000 | 5300000 | 5000000 |  |  |  | 5000000 | 5000000 |  |  |  | 5000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 15300000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.40 | Design/ Construction | City of Torrance Pacific Coast Highway (SR-1) at Vista Montana/Anza Ave Intersection Improvement | 2900000 | 2900000 | 900000 | 500000 | 500000 | 500000 | 500000 | 2000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2900000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.58 | Design/ Construction | City of Torrance Pacific Coast Highway (SR-1) from Calle Mayor to Janet Ln. safety improvement. | 852000 | 852000 | 200000 | 200000 | 200000 | 252000 |  | 652000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 852000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.59 | Design/ Construction | City of Torrance PCH at Madison Ave- Signal Upgrades to provide left-turn phasing | 500000 | 500000 | 100000 | 400000 |  |  |  | 400000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 500000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.60 | Design/ Construction | City of Torrance Crenshaw Blvd. from Del Amo to Dominguez; three Southbound turn lanes at 1) Del Amo Blvd; 2) extension of 208th St; 3) Transit Center Entrance. Signal Improvements at two existing and new signal at Transit Center and extension of 208th St. | 3300000 | 3300000 | 1300000 | 1000000 | 1000000 |  |  | 2000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3300000 | Total Cost |  | 100% EA |  | 100%
COMMITTED PROJECTS
COMMITTED MR312.47 | Construction | City of Hawthorne Prairie Ave from 118th St to Marine Ave- Signal Improvements | 1237000 | 1237000 |  |  |  |  | 204114 | 204114 | 204114 | 204114 | 204114 | 204114 | 816456 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1237000 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.50 | Construction | City of Inglewood Citywide ITS Phase V- Communication gap closure on various locations, TS upgrade and arterial detection | 384000 | 384000 | [5 empty] | 0 | 14000 | 14000 | 14000 | 109000 | 151000 | 58250 | 58250 | 58250 | 58250 | 233000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 384000 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.53 | Construction | City of Lawndale Redondo Beach Blvd. Mobility Improvements from Prairie to Artesia (PSRE) at I-405, from Hawthorne Bl. to Prairie Ave- PS&E / ROW Acquisition; Signal upgrades, concrete pads for transit, ADA ramps | 1039262 | 1039262 | [5 empty] | 0 | 129908 | 129908 | 129908 | 129908 | 519632 | 129908 | 129908 | 129908 | 129908 | 519632 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1039262 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.51 | Construction | City of Los Angeles Anaheim St from Farragut Ave to Dominguez Channel- Widen from 78' to 84' and restripe to accommodate an additional lane in each direction | 3141450 | 3141450 |  | 150000 | 150000 | 150000 | 150000 | 600000 | 150000 | 150000 | 150000 | 150000 | 600000 | 500000 | 500000 | 500000 | 441450 | 1941450 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3141450 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.52 | Construction | Los Angeles County 2013 CFP South Bay Forum systemwide operational improvements, coordination and timing, and ITS improvements | 1021000 | 1021000 | [5 empty] | 0 |  |  |  |  | 0 | 10000 | 15000 | 25000 | 50000 | 100000 | 40000 | 50000 | 60000 | 90000 | 240000 | 100000 | 120000 | 140000 | 140000 | 500000 | 30000 | 50000 | 50000 | 50681 | 180681 | 1021000 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.34 | Construction | City of Manhattan Beach Construct SB and WB right-turn lanes on Aviation at Artersia. The project will include right-of-way acquisition, utility relocation, street widening and restriping of the northwest corner of the Aviation Blvd. and Artesia Blvd. intersection. | 1500000 | 1500000 | 151000 | 369000 | 78000 | 602000 | 300000 | 1349000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1500000 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.35 | Construction | City of Manhattan Beach Sepulveda Blvd (SR-1) at Manhattan Beach Blvd Intersection Improvement. Add left-turn lanes. The project will include right-of-way acquisition, utility relocation, street widening and restriping of the intersection. | 980000 | 980000 |  | 11000 | 54800 | 34000 | 50000 | 149800 | 50000 | 48000 | 244000 | 244000 | 586000 | 244200 |  |  |  | 244200 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 980000 | Total Cost |  | 100% EA |  | 100%
COMMITTED PROJECT MR312.09 | PD/EA and PS&E | City of Torrance Pacific Coast Highway (SR-1) and Crenshaw Ave- Preliminary Design, EIR and P.S.&E. for operational improvements | 1300000 | 1300000 |  |  |  |  | 1300000 | 1300000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 6500000 | Placeholder Est. |  | 100% EA |  | 100%
COMMITTED MRE312.# | PS&E | City of Torrance Hawthorne Bl (SR-107) at: 182nd Street, Spencer Street, Emerald Street, and Lomita Blvd. P.S.&E for roadway widening to construct new northbound right turn lanes | 810000 | 810000 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | - | Construction Cost Est. Separate |  | 100% EA |  | 100%
NEW REQUEST FOR PROJECTS
Requested | Design/ Construction | City of Carson Widen Sepulveda Blvd for 1,475 linear feet to provide three lanes of traffic in both directions and a raised median, the project involves widening the bridge over the Dominguez Channel. | 6375903 | 5500722.4 |  | 687590.4078 | 491135.8824 | 2750361.6314 | 1571635.3412 | 5500723.2627 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 6375903 | Total Cost | Eligible - Nexus Project | 80% | No | 86.27%
Requested | Design/ Construction | City of Carson Victoria St at Tamcliff Ave - Installation of left-turn phases. | 120000 | 120000 |  | 30000 | 30000 | 30000 | 30000 | 120000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 120000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Carson 223rd St from Lucerne Ave to Alameda St.: widening roadway and install median. | 3601766 | 3281412.8 |  | 410176.8278 | 410176.8278 | 410176.8278 | 410176.8278 | 1640707.3111 | 410176.8278 | 410176.8278 | 410176.8278 | 410176.8278 | 1640707.3111 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3601766 | Total Cost | Eligible, enhancement portion is $100k (3%) | 80% | No | 91.11%
Requested | Design/ Construction | City of Carson Figueroa St. at 234th St. - Upgrade the traffic signal equipment to modernize the controller and signal lights | 150000 | 150000 |  | 37500 | 37500 | 37500 | 37500 | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 150000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested |  | City of Carson Traffic Signal Upgrade at Intersection of 213th Street and Dolores Street | 150000 | 150000 | [5 empty] | 0 |  |  |  |  | 0 | 37500 | 37500 | 37500 | 37500 | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 150000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Carson Traffic Signal upgrades at 10 intersections: Figueroa St. at Victoria St., Main St. at 220th St., Main St. at Victoria St., Main St. at Albertoni St., Figueroa St. at 223rd St., Broadway at Victoria St., Albertoni St., Gardena Blvd., Alondra Blvd. and a midblock crossing south of Albertoni Blvd. | 1400000 | 1400000 |  | 187500 | 37500 | 37500 | 37500 | 300000 | 37500 | 37500 | 37500 | 37500 | 150000 | 37500 | 37500 | 37500 | 37500 | 150000 | 200000 | 200000 | 200000 | 200000 | 800000 |  |  |  |  | 0 |  |  |  |  | 0 | 1400000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Gardena Crenshaw Bl from El Segundo Bl to Redondo Beach Bl - Arterial Improvements, traffic signal upgrades and synchronization, add turn pockets where feasible, traffic channelization. | 1900000 | 1900000 |  |  |  | 58000 | 58000 | 116000 | 57000 | 575000 | 576000 | 576000 | 1784000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1900000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Gardena Redondo Beach Bl from Crenshaw Bl to Vermont Ave - Arterial Improvements, traffic signal upgrades and synchronization, add turn pockets where feasible, traffic channelization. | 3600000 | 3280000 |  |  |  |  | 25511.1111 | 25511.1111 | 24600 | 61955.5556 | 61955.5556 | 61955.5556 | 210466.6667 | 61955.5556 |  | 994022.2222 | 994022.2222 | 2050000 | 994022.2222 |  |  |  | 994022.2222 |  |  |  |  | 0 |  |  |  |  | 0 | 3600000 | Total Cost | Eligible - Nexus Project | 80% | No | 91.11%
Requested | Design/ Construction | City of Gardena Normandie Ave from El Segundo Bl to 177th St - Arterial Improvements, traffic signal upgrades and synchronization, add turn pockets where feasible, traffic channelization, transit access. | 4000000 | 3600000 |  |  |  | 108900 | 108900 | 217800 | 108900 | 818100 | 819000 | 818100 | 2564100 | 818100 |  |  |  | 818100 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4000000 | Total Cost | Eligible - Nexus Project | 80% | No | 90%
Requested | Design/ Construction | City of Gardena Van Ness Ave from El Segundo Bl to Redondo Beach Bl - Arterial Improvements, traffic signal upgrades and synchronization, add turn pockets where feasible, traffic channelization. | 3000000 | 2800000 |  |  |  | 124133.3333 | 130666.6667 | 254800 | 636533.3333 | 636533.3333 | 636533.3333 | 635600 | 2545200 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3000000 | Total Cost | Eligible - Nexus Project | 80% | No | 93.33%
Requested | Design/ Construction | City of Gardena Artesia Bl from Western Ave to Vermont Ave - Arterial Improvements, traffic signal upgrades and synchronization, add turn pockets, traffic channelization. | 2654000 | 2523200 |  |  |  | 77007.9879 | 76057.272 | 153065.26 | 76057.272 | 758671.2886 | 757720.5727 | 757720.5727 | 2350169.7061 | 19965.0339 |  |  |  | 19965.0339 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2654000 | Total Cost | Eligible - Nexus Project | 80% | No | 95.07%
Requested | Design/ Construction | City of Gardena Rosecrans Ave at Vermont Ave & Redondo Beach Bl at Vermont Ave - Traffic Signal upgrades and synchronization, add turn pockets, traffic channelization. | 1500000 | 1500000 |  |  |  | 20000 | 38000 | 58000 | 38000 | 38000 | 456000 | 455000 | 987000 | 455000 |  |  |  | 455000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1500000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Hawthorne Inglewood Ave at El Segundo Bl, Crenshaw Bl at Rocket Road & Crenshaw Bl at Jack Northrop - Intersection widening improvements & traffic signal modifications | 2000000 | 2000000 |  |  | 500000 | 600000 | 900000 | 2000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2000000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Hawthorne Hawthorne Bl from 120th St to 111th St - Arterial Improvements | 5000000 | 4400000 |  |  |  | 400000 | 700000 | 1100000 | 500000 | 1000000 | 800000 | 1000000 | 3300000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 5000000 | Total Cost | Eligible - Nexus Project | 80% | Yes | 88%
Requested | Design/ Construction | City of Hawthorne El Segundo Blvd. from Hawthorne Blvd. to Crenshaw Bl - Upgrade signals, improve right and left-turn lanes | 3000000 | 2800000 |  |  |  | 100000 | 400000 | 500000 | 300000 | 1000000 | 1000000 |  | 2300000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3000000 | Total Cost | Eligible - Nexus Project | 80% | Yes | 93.33%
Requested | Design/ Construction | City of Manhattan Beach Sepulveda Bl at Rosecrans Ave, 33rd St, Cedar Ave, 14th St & 2nd St - Operational Improvements. | 900000 | 900000 |  |  | 30000 | 30000 | 30000 | 90000 | 5000 | 5000 | 270000 | 270000 | 550000 | 260000 |  |  |  | 260000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 900000 | Total Cost | Eligible | 100% | Yes | 100%
Requested | Design/ Construction | Los Angeles County Wilmington Ave north of Del Amo Blvd.: Construct safety improvements at railroad crossing | 600000 | 600000 |  |  |  | 25000 | 25000 | 50000 | 50000 | 25000 | 25000 | 450000 | 550000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 600000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
COMPLETED FEASIBILITY/PLANNING STUDIES
Completed TO 2014-3 A-F | Feasibility Study | City of Gardena Feasibility Studies for 2015 Metro CFP | 42632 | 42632 | 42632 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 852640 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 9.5 | Feasibility Study | City of Gardena PSRE for three park and ride facilities | 11920 | 11920 | 11920 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 238400 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 9.2 | Feasibility Study | City of Hawthorne PSRE for Signal and associated improvements on Prairie Ave from 118th St. to Marine Ave. | 32643 | 32643 | 32643 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 652860 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBPH TO 2014-5 | Feasibility Study | City of Hermosa Beach PSR for Pacific Coast Highway (SR-1) / Aviation Blvd. Mobility Improvements Project | 190000 | 190000 | 190000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3800000 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBPH TO 9.3 | Feasibility Study | City of Inglewood PSRE for geometric improvements on La Cienega Blvd and Manchester Blvd. | 31664 | 31664 | 31664 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3166400 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 9.4 | Feasibility Study | City of Inglewood PSRE for Phase V of Inglewood's ITS Upgrades | 24434 | 24434 | 24434 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | - | Construction Cost Separate |  | 100% EA |  | 100%
Completed SBHP TO 2014-4 | Feasibility Study | City of Inglewood PSR for Manchester/La Cienega Bundled Projects: channelize and raise median Manchester Boulevard from Ash Avenue to La Cienega Boulevard, improve turn radii La Cienega Boulevard at Manchester Boulevard, improve turn radii and through-right lane La Cienega Boulevard at Florence Avenue | 23625 | 23625 | 23625 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2362500 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 2014-6 | Feasibility Study | City of Lawndale PSRE for Redondo Beach Blvd. Mobility Improvements from Prairie Ave. to Artesia Blvd. at I-405, from Hawthorne Bl. to Prairie Ave. Signal upgrades, concrete pads for transit, ADA ramps | 47360 | 47360 | 47360 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4736000 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 2014-7 | Feasibility Study | City of Manhattan Beach PSR for 7 intersections along Sepulveda Blvd (SR-1) corridor that were identified in the 2009 PCH Study conducted by SCAG and the SBCCOG: at Rosecrans., Marine Ave. / Cedar Ave., Valley Dr., 33rd St., 30th St., 14th St., and 2nd St. | 43043 | 43043 | 43043 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4304300 | Placeholder Est. |  | 100% EA |  | 100%
Completed Feas Study | Feasibility Study | Metro South Bay Baseline Arterial Performance Monitoring Implementation Study | 250000 | 250000 | 250000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 250000 | Complete |  | 100% EA |  | 100%
Completed SBHP TO 9.1 | Feasibility Study | City of Torrance PSRE for additional turn lanes on Western Ave. (SR-213) at Sepulveda Blvd. | 37921 | 37921 | 37921 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1896050 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 2014-2A | Feasibility Study | City of Torrance Western Ave (SR-213) at Sepulveda Blvd Intersection Improvements | 80000 | 80000 | 80000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4000000 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 2014-2B | Feasibility Study | City of Torrance PSR for Hawthorne Blvd. (SR-107) Corridor Improvements at Lomita Blvd, Emerald, Spencer, and 182nd Streets | 70000 | 70000 | 70000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3500000 | Placeholder Est. |  | 100% EA |  | 100%
COMPLETED PROJECTS
Completed MR312.22 D, C | Construction | City of El Segundo Maple Ave Arterial Improvements from Sepulveda Blvd to Parkview Ave | 2500000 | 2500000 | 2157575 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2500000 | Total Cost |  | 100% EA |  | 100%
Completed MR312.19 PD, D, C | Construction | City of Gardena Artesia Blvd at Western Ave Intersection Improvements (WB Left Turn Lanes) | 600000 | 600000 | 431825 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 600000 | Total Cost |  | 100% EA |  | 100%
Completed MR312.21 |  | City of Gardena Vermont Arterial Improvement From Rosecrans Ave to 182nd Street | 2350000 | 2350000 | 2350000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2350000 | Total Cost |  | 100% EA |  | 100%
Completed MR312.03 | Construction | City of Hawthorne Rosecrans Ave Arterial Improvements from I-405 SB Off-Ramp to Isis Ave | 2100000 | 2100000 | 2100000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2100000 | Total Cost |  | 100% EA |  | 100%
Completed MR312.44 |  | City of Hawthorne Hawthorne Blvd From El Segundo Blvd. to Rosecrans Ave | 7551000 | 7551000 | 7551000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 7551000 | Total Cost |  | 100% EA |  | 100%
Completed MR312.13 | Construction | City of Redondo Beach Aviation Blvd at Artesia Blvd Intersection Imp. | 22000 | 22000 | 19281.04 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 22000 | Total Cost |  | 100% EA |  | 100%
Completed MR312.14 | Construction | City of Redondo Beach Inglewood Ave at Manhattan Beach Blvd Intersection Improvements | 30000 | 30000 | 27122 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 30000 | Total Cost |  | 100% EA |  | 100%
Completed MR312.18 | Construction | City of Torrance Maple Ave at Sepulveda Blvd. Intersection Improvements | 540000 | 540000 | 319870.46 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 540000 | Total Cost |  | 100% EA |  | 100%
|  | TOTALS | 253169842.09 | 227824508.29 | 80621267.59 | 17157369.2356 | 11569152.7101 | 15455452.7804 | 18933934.2188 | 63115908.9449 | 9289914.4331 | 7398834.0053 | 7383783.2894 | 7055949.956 | 31365505.6838 | 3516628.5895 | 2017408 | 3877430.2222 | 4897630.2222 | 14826855.0339 | 3810522.2222 | 1826500 | 572500 | 2422500 | 9608263.2222 | 3201250 | 3221250 | 3241250 | 3241250 | 13859978 | 3125250 | 3145250 | 3144250 | 3144931 | 13613658 | 520730747.09

## Exhibit B
Exhibit B: Life of Project Cost Magnitudes
|  | Updated: 10/20/15 |  |  |  | 2016-2017 (FY 17) |  |  |  |  | 2017-2018 (FY 18) |  |  |  | Future Years | 2018-2019 (FY 19) |  |  |  |  | 2019-2020 (FY 20) |  |  |  |  | 2020-2021 (FY 21) |  |  |  |  | 2021-2022 (FY 22) |  |  |  |  | Total Project Est. Cost |  | Eligibility and Matching Policy
Metro Project ID FA Type | Phase | Lead Agency / Description | Phase Cost | Measure R Share | Est. Reimburse. by 6/30/16 | Q1 16-17 July-Sept | Q2 16-17 Oct-Dec | Q3 16-17 Jan-March | Q4 16-17 April-June | 16-17 TOTAL | Q1 17-18 July-Sept | Q2 17-18 Oct-Dec | Q3 17-18 Jan-March | Q4 17-18 April-June | 17-18 TOTAL | Q1 18-19 July-Sept | Q2 18-19 Oct-Dec | Q3 18-19 Jan-March | Q4 18-19 April-June | 18-19 TOTAL | Q1 19-20 July-Sept | Q2 19-20 Oct-Dec | Q3 19-20 Jan-March | Q4 19-20 April-June | 19-20 TOTAL | Q1 20-21 July-Sept | Q2 20-21 Oct-Dec | Q3 20-21 Jan-March | Q4 20-21 April-June | 20-21 TOTAL | Q1 21-22 July-Sept | Q2 21-22 Oct-Dec | Q3 21-22 Jan-March | Q4 21-22 April-June | 21-22 TOTAL | Total Project Est. Cost (All Phases and Sources) | Total Cost Est. Source | Eligibility | Measure R Percent | Measure R Revised by Lead Agency? | MBR Measure R Share
ADMINISTRATIVE
Administration & Miscellaneous Expense |  |  | 1022958.68 | 1022958.68 | 840930.68 | 7035 | 7035 | 7035 | 7035 | 28140 | 7247 | 7247 | 7247 | 7247 | 28988 | 7463 | 7463 | 7463 | 7463 | 29852 | 7688 | 7688 | 7688 | 7688 | 30752 | 7918 | 7918 | 7918 | 7918 | 31672 | 8156 | 8156 | 8156 | 8156 | 32624 |  |  |  | 100% |  | 100%
Program Development and Misc. Expenses (development, oversight, and intergovernmental relations) |  |  | 5696599.02 | 5696599.02 | 2439624.02 | 129595 | 129596 | 129597 | 129597 | 518385 | 140134 | 140134 | 140134 | 140134 | 560536 | 121975 | 121977 | 121977 | 121977 | 487906 | 136371 | 136372 | 136373 | 136373 | 545489 | 130825 | 130827 | 130827 | 130827 | 523306 | 155337 | 155338 | 155339 | 155339 | 621353 | 17577216.09 | All Admin |  | 100% |  | 100%
Feasibility Studies (previous reimbursement) |  |  | 1696661.39 | 1696661.39 | 496661.39 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 400000 |  |  |  |  | 400000 |  |  |  |  | 400000 | [5 empty] | 100%
ACTIVE FEASIBLITY/PLANNING STUDIES
EXECUTED MR312.57 PD | Feasibility Study | City of El Segundo Park Place from Nash St. to Allied Way, Roadway extension and railroad grade separation | 350000 | 350000 | 150000 |  | 150000 |  |  | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 35850000 | From Lead Agency |  | 50% | Future Funding Mix Not Identified | 100%
EXECUTED FEAS STUDY SBHP TO 2015-1 | Feasibility Study | Port of LA Vincent Thomas Bridge (SR-47) I-110 Connector | 1000000 | 1000000 | 112000 | 290000 | 314000 | 234000 | 50000 | 888000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1000000 | Construction Separate |  | 100% EA |  | 100%
EXECUTED MR312.24 | PA/ED | Caltrans PAED I-110 Auxiliary lane from SR-91 to Torrance Blvd Auxiliary lane & 405/110 Connector | 1500000 | 1500000 | 1500000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 30000000 | Placeholder Est. |  | 50% | Future Funding Mix Not Identified | 100%
EXECUTED MR312.25 | PA/ED | Caltrans PAED I-405 at 182nd St./Crenshaw Boulevard | 1700000 | 1700000 | 1700000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 34000000 | Placeholder Est. |  | 50% | Future Funding Mix Not Identified | 100%
EXECUTED MR312.56 | PA/ED | City of Los Angeles Review of Feas. Study on Del Amo Blvd from Western Ave to Vermont Ave. | 100000 | 100000 | 3277 | 24180.75 | 24180.75 | 24180.75 | 24180.75 | 96723 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3000000 | Placeholder Est. |  | 80% | Future Funding Mix Not Identified | 100%
EXECUTED MR312.16 | PA/ED | Los Angeles County Del Amo Boulevard from Normandie Boulevard to Vermont Ave | 1900000 | 1900000 | 1900000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 26000000 | Placeholder Est. |  | 50% | Future Funding Mix Not Identified | 100%
COMMITTED FEASIBLITY/PLANNING STUDIES
COMMITTED MR312.30 | Feasibility Study | Caltrans I-405 from I-110 to I-105 and I-105 from I-405 to Crenshaw: Corridor Refinement Studies | 700000 | 700000 |  | 75000 | 75000 | 75000 | 75000 | 300000 | 100000 | 100000 | 100000 | 100000 | 400000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 14000000 | Placeholder Est. |  | 100% EA | Future Funding Mix Not Identified | 100%
COMMITTED MR312.45 | PA/ED | Caltrans PAED/Implement an Integrated Corridor Management System along the SR -110 Corridor between Artesia Boulevard and the I-405. The project will integrate freeway, arterial and transit operations, implement a Decision Support System for coordinated agency operations and traveler information systems. | 1000000 | 1000000 | [5 empty] | 0 |  |  |  |  | 0 | 125000 | 125000 | 125000 | 125000 | 500000 | 125000 | 125000 | 125000 | 125000 | 500000 |  |  |  |  | 0 |  |  |  |  | 0 | 20000000 | Placeholder Est. |  | 100% EA | Future Funding Mix Not Identified | 100%
COMMITTED SBHP TO 2014-1 | Feasibility Study | City of El Segundo Aviation Blvd, Douglas St. and El Segundo Blvd. Commuter Bikeways Study | 150000 | 150000 |  |  | 150000 |  |  | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3000000 | Placeholder Est. |  | 100% EA | Future Funding Mix Not Identified | 100%
COMMITTED FEAS STUDY SBHP TO #-# | Feasibility Study | City of Torrance Pacific Coast Highway (SR-1) / Hawthorne Blvd. (SR-107) Park & Ride Feasibility Study | 150000 | 150000 | [5 empty] | 0 | 150000 |  |  |  | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3000000 | Placeholder Est. |  | 100% EA | Future Funding Mix Not Identified | 100%
COMMITTED FEAS STUDY SBHP TO #-# | Feasibility Study | City of Torrance 182nd St from Kingsdale Ave to Harbor Gateway Transit Center (e/o Vermont Ave.): feasibility of study various corridor improvements (intersection improvements, ITS, bicycle facilities, etc.). | 300000 | 300000 |  |  |  | 300000 |  | 300000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 6000000 | Placeholder Est. |  | 100% EA | Future Funding Mix Not Identified | 100%
NEW REQUEST FOR FEASIBILITY/PLANNING STUDIES
Requested | Feasibility Study | Caltrans I-405 from I-110 to I-105 (including a mile on either side of the freeway): Identify and prioritize operational improvements (aux. lanes, interchange configuration) to reduce travel delay. | 700000 | 700000 |  | 50000 | 50000 | 75000 | 75000 | 250000 | 75000 | 75000 | 75000 | 75000 | 300000 | 75000 | 75000 |  |  | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 14000000 | Placeholder Est. | Eligible | 100% |  | 100%
Requested | PSR | Caltrans SR-1 from eastern boundary of Carson to eastern boundary of Torrance - PSR | 170000 | 170000 |  |  |  | 85000 | 85000 | 170000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3400000 | Placeholder Est. | Eligible | 100% |  | 100%
Requested | PSR | Caltrans Western Ave.(SR-213) from Palos Verdes Drive North to northern boundary of Gardena - PSR | 170000 | 170000 |  |  |  | 85000 | 85000 | 170000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3400000 | Placeholder Est. | Eligible | 100% |  | 100%
Requested | Feasibility Study | City of Carson Avalon Boulevard Bridge over the Dominguez Channel: Investigate feasibility of an additional lane on the west side for a bike lane and widening of the east side sidewalk to improve flow in a constrained location. | 60000 | 60000 | [5 empty] | 0 | 60000 |  |  |  | 60000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 5000000 | Placeholder Est. | Eligible | 100% |  | 100%
Requested | PA/ED | City of El Segundo PA/ED Park Place from Nash St to Allied Way- Roadway extension and railroad grade separation, including utility and railroad relocation and construction. | TBD | TBD |  |  |  | 1000000 |  | 1000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | - | Design/Const Separate | Eligible - Nexus Project |  |  | 100%
Requested | PA/ED + Est Const./ ROW funding | City of Hermosa Beach PA/ED Aviation Bl from PCH to Prospect Ave - Arterial Improvements. | $1,800,000 PA/ED, $42m Cost/ROW | 22300000 |  |  |  | 1800000 |  | 1800000 |  |  |  |  | 0 | 273000 | 273000 | 894000 | 894000 | 2334000 | 894000 | 894000 |  | 1820000 | 3608000 | 1820000 | 1820000 | 1820000 | 1820000 | 7280000 | 1820000 | 1820000 | 1819000 | 1819000 | 7278000 | 44599000 | From Lead Agency | Eligible with Nexus Project elements | 100% | Yes | 50%
Requested | PA/ED | City of Inglewood PA/ED for Florence Ave at La Brea Ave - Construct new Downtown Inglewood Transit Center at La Brea Station of Crenshaw Line | 1500000 | 1500000 |  | 30000 | 30000 | 30000 | 30000 | 120000 | 30000 | 213750 | 213750 | 213750 | 671250 | 213750 | 213750 | 213750 | 67500 | 708750 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1500000 | Total Cost | Eligible, bus turnouts and demand reduction | 100% |  | 100%
Requested | PA/ED | Port of LA PA/ED for SR-47/Vincent Thomas Bridge and Front St/Harbor Bl Interchange Reconfiguration. | 12078500 | 12078500 | [5 empty] | 0 | 88125 | 88125 | 88125 | 88125 | 352500 | 187500 | 187500 | 187500 | 187500 | 750000 | 187500 | 187500 | 187500 | 187500 | 750000 | 1281250 | 1281250 | 1281250 | 1281250 | 5125000 | 1275250 | 1275250 | 1275250 | 1275250 | 5101000 | 23452000 | From Lead Agency | Eligible | 50% | Yes | 51.5%
Requested | Feasibility Study | City of Rancho Palos Verdes Western Ave (SR-213) from Palos Verdes Drive North to 25th St,: Feasibility study for improvements in coordination with Lomita, LADOT, and Caltrans. | 90000 | 90000 |  | 25000 | 15000 | 30000 | 20000 | 90000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1800000 | Placeholder Est. | Eligible | 100% |  | 100%
ACTIVE PROJECTS
EXECUTED MR312.11 | Design/ Construction | Caltrans ITS: I-405, I-110, I-105, SR-91 at freeways ramp/arterial signalized intersections - DCCM | 5000000 | 5000000 | 5000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 25000000 | Placeholder Est. |  | 100% EA |  | 100%
EXECUTED MR312.29 | Design/ Construction | Caltrans Pacific Coast Highway (SR-1) ITS with parallel arterials from I-105 to I-110 | 9000000 | 9000000 | 5472000 | 1250000 | 850000 | 728000 | 700000 | 3528000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 9000000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.37 | Design/ Construction | City of Carson Sepulveda Boulevard widening from Alameda Street to ICTF Driveway | 1158000 | 1158000 | 1158000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1158000 | Total Cost |  | 100% |  | 100%
EXECUTED MR312.17 | Design/ Construction | City of Gardena Rosecrans Ave Arterial Improvements From Vermont Ave to Crenshaw Blvd. | 5140000 | 5140000 | 1907759 | 808060.25 | 808060.25 | 808060.25 | 808060.25 | 3232241 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 5140000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.33 | Design/ Construction | City of Hawthorne Aviation Bl at Marine Ave; construct westbound right-turn lane. | 3600000 | 3600000 | 155000 | 145000 | 125000 | 25000 | 50000 | 345000 | 15000 | 30000 | 25000 | 230000 | 300000 |  |  | 300000 | 1500000 | 1800000 | 1000000 |  |  |  | 1000000 |  |  |  |  | 0 |  |  |  |  | 0 | 3600000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.05 | Design/ Construction | City of Hermosa Beach Pacific Coast Highway (SR-1) between Anita St and Artesia Blvd: Improvements | 304000 | 304000 | 202936 | 101063 |  |  |  | 101063 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 304000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.12 | Design/ Construction | City of Inglewood Citywide ITS Phase IV | 3500000 | 3500000 | 3500000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3500000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.15 | Design/ Construction | City of Lawndale Inglewood Ave From 156th st to I-405 SB On Ramp Improvements | 500000 | 500000 | 500000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 500000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.36 | Construction | City of Lawndale Traffic Signal Improvements Citywide | 1500000 | 1500000 | 1500000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1500000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.43 | Design/ Construction | City of Lomita Intersection Improvements at Western (SR-213) /Palos Verdes Dr. & Pacific Coast Highway (SR-1)/Walnut | 900000 | 900000 | 800000 | 100000 |  |  |  | 100000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 900000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.28 | Construction | City of Manhattan Beach Seismic retrofit of Sepulveda Blvd (SR-1) bridge 53-62 | 9100000 | 9100000 | 6461664 | 1319168 | 1319168 |  |  | 2638336 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 9100000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.04 | Construction | City of Manhattan Beach Sepulveda Blvd at Marine Ave (WB Left Turn Lane) | 365000 | 365000 | 364500 | 500 |  |  |  | 500 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 365000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.06 | Design/ Construction | City of Redondo Beach Pacific Coast Highway (SR-1) Arterial Improvements from Anita St to Palos Verdes Blvd | 1400000 | 1400000 | 150000 | 75000 | 115000 | 30000 | 280000 | 500000 | 250000 | 250000 | 250000 |  | 750000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1400000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.07 | Construction | City of Redondo Beach Pacific Coast Highway (SR-1) at Torrance Blvd Intersection Improvements | 585000 | 585000 | 127000 | 10000 | 148000 | 150000 | 150000 | 458000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 585000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.08 | Design/ Construction | City of Redondo Beach Pacific Coast Highway (SR-1) at Palos Verdes Blvd Intersection Improvements | 320000 | 320000 | 320000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 320000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.20 | Design/ Construction | City of Redondo Beach Aviation Blvd at Artesia Blvd Intersection Improvements | 847000 | 847000 | 350000 | 165000 | 172000 | 160000 |  | 497000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 847000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.42 | Design/ Construction | City of Redondo Beach Inglewood Ave at Manhattan Beach Bl: Add SB right-turn lane south of railroad tracks to Manhattan Beach Bl | 5175000 | 5175000 | 117000 | 70000 | 68000 | 733000 | 782000 | 1653000 | 730000 | 730000 | 40000 | 40000 | 1540000 | 10000 | 365000 | 375000 | 375000 | 1125000 | 370000 | 370000 |  |  | 740000 |  |  |  |  | 0 |  |  |  |  | 0 | 5175000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.10 | Design/ Construction | City of Torrance Pacific Coast Highway (SR-1) at Hawthorne Blvd (SR-107) Intersection Improvements | 19600000 | 19600000 | 9600000 | 500000 | 500000 | 500000 | 8500000 | 10000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 19600000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.23 | Design/ Construction | City of Torrance Torrance Park and Ride Regional Terminal | 18100000 | 18100000 | 10000000 | 3000000 | 3000000 | 2100000 |  | 8100000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 18100000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.26 | Design/ Construction | City of Torrance I-405 at 182nd St. /Crenshaw Blvd. operational improvements | 15300000 | 15300000 | 5300000 | 5000000 |  |  |  | 5000000 | 5000000 |  |  |  | 5000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 15300000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.40 | Design/ Construction | City of Torrance Pacific Coast Highway (SR-1) at Vista Montana/Anza Ave Intersection Improvement | 2900000 | 2900000 | 900000 | 500000 | 500000 | 500000 | 500000 | 2000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2900000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.58 | Design/ Construction | City of Torrance Pacific Coast Highway (SR-1) from Calle Mayor to Janet Ln. safety improvement. | 852000 | 852000 | 200000 | 200000 | 200000 | 252000 |  | 652000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 852000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.59 | Design/ Construction | City of Torrance PCH at Madison Ave- Signal Upgrades to provide left-turn phasing | 500000 | 500000 | 100000 | 400000 |  |  |  | 400000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 500000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.60 | Design/ Construction | City of Torrance Crenshaw Blvd. from Del Amo to Dominguez; three Southbound turn lanes at 1) Del Amo Blvd; 2) extension of 208th St; 3) Transit Center Entrance. Signal Improvements at two existing and new signal at Transit Center and extension of 208th St. | 3300000 | 3300000 | 1300000 | 1000000 | 1000000 |  |  | 2000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3300000 | Total Cost |  | 100% EA |  | 100%
COMMITTED PROJECTS
COMMITTED MR312.47 | Construction | City of Hawthorne Prairie Ave from 118th St to Marine Ave- Signal Improvements | 1237000 | 1237000 |  |  |  |  | 204114 | 204114 | 204114 | 204114 | 204114 | 204114 | 816456 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1237000 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.50 | Construction | City of Inglewood Citywide ITS Phase V- Communication gap closure on various locations, TS upgrade and arterial detection | 384000 | 384000 | [5 empty] | 0 | 14000 | 14000 | 14000 | 109000 | 151000 | 58250 | 58250 | 58250 | 58250 | 233000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 384000 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.53 | Construction | City of Lawndale Redondo Beach Blvd. Mobility Improvements from Prairie to Artesia (PSRE) at I-405, from Hawthorne Bl. to Prairie Ave- PS&E / ROW Acquisition; Signal upgrades, concrete pads for transit, ADA ramps | 1039262 | 1039262 | [5 empty] | 0 | 129908 | 129908 | 129908 | 129908 | 519632 | 129908 | 129908 | 129908 | 129908 | 519632 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1039262 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.51 | Construction | City of Los Angeles Anaheim St from Farragut Ave to Dominguez Channel- Widen from 78' to 84' and restripe to accommodate an additional lane in each direction | 3141450 | 3141450 |  | 150000 | 150000 | 150000 | 150000 | 600000 | 150000 | 150000 | 150000 | 150000 | 600000 | 500000 | 500000 | 500000 | 441450 | 1941450 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3141450 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.52 | Construction | Los Angeles County 2013 CFP South Bay Forum systemwide operational improvements, coordination and timing, and ITS improvements | 1021000 | 1021000 | [5 empty] | 0 |  |  |  |  | 0 | 10000 | 15000 | 25000 | 50000 | 100000 | 40000 | 50000 | 60000 | 90000 | 240000 | 100000 | 120000 | 140000 | 140000 | 500000 | 30000 | 50000 | 50000 | 50681 | 180681 | 1021000 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.34 | Construction | City of Manhattan Beach Construct SB and WB right-turn lanes on Aviation at Artersia. The project will include right-of-way acquisition, utility relocation, street widening and restriping of the northwest corner of the Aviation Blvd. and Artesia Blvd. intersection. | 1500000 | 1500000 | 151000 | 369000 | 78000 | 602000 | 300000 | 1349000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1500000 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.35 | Construction | City of Manhattan Beach Sepulveda Blvd (SR-1) at Manhattan Beach Blvd Intersection Improvement. Add left-turn lanes. The project will include right-of-way acquisition, utility relocation, street widening and restriping of the intersection. | 980000 | 980000 |  | 11000 | 54800 | 34000 | 50000 | 149800 | 50000 | 48000 | 244000 | 244000 | 586000 | 244200 |  |  |  | 244200 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 980000 | Total Cost |  | 100% EA |  | 100%
COMMITTED PROJECT MR312.09 | PD/EA and PS&E | City of Torrance Pacific Coast Highway (SR-1) and Crenshaw Ave- Preliminary Design, EIR and P.S.&E. for operational improvements | 1300000 | 1300000 |  |  |  |  | 1300000 | 1300000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 6500000 | Placeholder Est. |  | 100% EA |  | 100%
COMMITTED MRE312.# | PS&E | City of Torrance Hawthorne Bl (SR-107) at: 182nd Street, Spencer Street, Emerald Street, and Lomita Blvd. P.S.&E for roadway widening to construct new northbound right turn lanes | 810000 | 810000 | [5 empty] | 0 | 810000 |  |  |  | 810000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | - | Construction Cost Est. Separate |  | 100% EA |  | 100%
NEW REQUEST FOR PROJECTS
Requested | Design/ Construction | City of Carson Widen Sepulveda Blvd for 1,475 linear feet to provide three lanes of traffic in both directions and a raised median, the project involves widening the bridge over the Dominguez Channel. | 6375903 | 5500722.4 |  | 687590.4078 | 491135.8824 | 2750361.6314 | 1571635.3412 | 5500723.2627 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 6375903 | Total Cost | Eligible - Nexus Project | 80% | No | 86.27%
Requested | Design/ Construction | City of Carson Victoria St at Tamcliff Ave - Installation of left-turn phases. | 120000 | 120000 |  | 30000 | 30000 | 30000 | 30000 | 120000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 120000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Carson 223rd St from Lucerne Ave to Alameda St.: widening roadway and install median. | 3601766 | 3281412.8 |  | 410176.8278 | 410176.8278 | 410176.8278 | 410176.8278 | 1640707.3111 | 410176.8278 | 410176.8278 | 410176.8278 | 410176.8278 | 1640707.3111 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3601766 | Total Cost | Eligible, enhancement portion is $100k (3%) | 80% | No | 91.11%
Requested | Design/ Construction | City of Carson Figueroa St. at 234th St. - Upgrade the traffic signal equipment to modernize the controller and signal lights | 150000 | 150000 |  | 37500 | 37500 | 37500 | 37500 | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 150000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested |  | City of Carson Traffic Signal Upgrade at Intersection of 213th Street and Dolores Street | 150000 | 150000 | [5 empty] | 0 |  |  |  |  | 0 | 37500 | 37500 | 37500 | 37500 | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 150000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Carson Traffic Signal upgrades at 10 intersections: Figueroa St. at Victoria St., Main St. at 220th St., Main St. at Victoria St., Main St. at Albertoni St., Figueroa St. at 223rd St., Broadway at Victoria St., Albertoni St., Gardena Blvd., Alondra Blvd. and a midblock crossing south of Albertoni Blvd. | 1400000 | 1400000 |  | 187500 | 37500 | 37500 | 37500 | 300000 | 37500 | 37500 | 37500 | 37500 | 150000 | 37500 | 37500 | 37500 | 37500 | 150000 | 200000 | 200000 | 200000 | 200000 | 800000 |  |  |  |  | 0 |  |  |  |  | 0 | 1400000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Gardena Crenshaw Bl from El Segundo Bl to Redondo Beach Bl - Arterial Improvements, traffic signal upgrades and synchronization, add turn pockets where feasible, traffic channelization. | 1900000 | 1900000 |  |  |  | 58000 | 58000 | 116000 | 57000 | 575000 | 576000 | 576000 | 1784000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1900000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Gardena Redondo Beach Bl from Crenshaw Bl to Vermont Ave - Arterial Improvements, traffic signal upgrades and synchronization, add turn pockets where feasible, traffic channelization. | 3600000 | 3280000 |  |  |  |  | 25511.1111 | 25511.1111 | 24600 | 61955.5556 | 61955.5556 | 61955.5556 | 210466.6667 | 61955.5556 |  | 994022.2222 | 994022.2222 | 2050000 | 994022.2222 |  |  |  | 994022.2222 |  |  |  |  | 0 |  |  |  |  | 0 | 3600000 | Total Cost | Eligible - Nexus Project | 80% | No | 91.11%
Requested | Design/ Construction | City of Gardena Normandie Ave from El Segundo Bl to 177th St - Arterial Improvements, traffic signal upgrades and synchronization, add turn pockets where feasible, traffic channelization, transit access. | 4000000 | 3600000 |  |  |  | 108900 | 108900 | 217800 | 108900 | 818100 | 819000 | 818100 | 2564100 | 818100 |  |  |  | 818100 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4000000 | Total Cost | Eligible - Nexus Project | 80% | No | 90%
Requested | Design/ Construction | City of Gardena Van Ness Ave from El Segundo Bl to Redondo Beach Bl - Arterial Improvements, traffic signal upgrades and synchronization, add turn pockets where feasible, traffic channelization. | 3000000 | 2800000 |  |  |  | 124133.3333 | 130666.6667 | 254800 | 636533.3333 | 636533.3333 | 636533.3333 | 635600 | 2545200 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3000000 | Total Cost | Eligible - Nexus Project | 80% | No | 93.33%
Requested | Design/ Construction | City of Gardena Artesia Bl from Western Ave to Vermont Ave - Arterial Improvements, traffic signal upgrades and synchronization, add turn pockets, traffic channelization. | 2654000 | 2523200 |  |  |  | 77007.9879 | 76057.272 | 153065.26 | 76057.272 | 758671.2886 | 757720.5727 | 757720.5727 | 2350169.7061 | 19965.0339 |  |  |  | 19965.0339 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2654000 | Total Cost | Eligible - Nexus Project | 80% | No | 95.07%
Requested | Design/ Construction | City of Gardena Rosecrans Ave at Vermont Ave & Redondo Beach Bl at Vermont Ave - Traffic Signal upgrades and synchronization, add turn pockets, traffic channelization. | 1500000 | 1500000 |  |  |  | 20000 | 38000 | 58000 | 38000 | 38000 | 456000 | 455000 | 987000 | 455000 |  |  |  | 455000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1500000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Hawthorne Inglewood Ave at El Segundo Bl, Crenshaw Bl at Rocket Road & Crenshaw Bl at Jack Northrop - Intersection widening improvements & traffic signal modifications | 2000000 | 2000000 |  |  | 500000 | 600000 | 900000 | 2000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2000000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Hawthorne Hawthorne Bl from 120th St to 111th St - Arterial Improvements | 5000000 | 4400000 |  |  |  | 400000 | 700000 | 1100000 | 500000 | 1000000 | 800000 | 1000000 | 3300000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 5000000 | Total Cost | Eligible - Nexus Project | 80% | Yes | 88%
Requested | Design/ Construction | City of Hawthorne El Segundo Blvd. from Hawthorne Blvd. to Crenshaw Bl - Upgrade signals, improve right and left-turn lanes | 3000000 | 2800000 |  |  |  | 100000 | 400000 | 500000 | 300000 | 1000000 | 1000000 |  | 2300000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3000000 | Total Cost | Eligible - Nexus Project | 80% | Yes | 93.33%
Requested | Design/ Construction | City of Manhattan Beach Sepulveda Bl at Rosecrans Ave, 33rd St, Cedar Ave, 14th St & 2nd St - Operational Improvements. | 900000 | 900000 |  |  | 30000 | 30000 | 30000 | 90000 | 5000 | 5000 | 270000 | 270000 | 550000 | 260000 |  |  |  | 260000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 900000 | Total Cost | Eligible | 100% | Yes | 100%
Requested | Design/ Construction | Los Angeles County Wilmington Ave north of Del Amo Blvd.: Construct safety improvements at railroad crossing | 600000 | 600000 |  |  |  | 25000 | 25000 | 50000 | 50000 | 25000 | 25000 | 450000 | 550000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 600000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
COMPLETED FEASIBILITY/PLANNING STUDIES
Completed TO 2014-3 A-F | Feasibility Study | City of Gardena Feasibility Studies for 2015 Metro CFP | 42632 | 42632 | 42632 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 852640 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 9.5 | Feasibility Study | City of Gardena PSRE for three park and ride facilities | 11920 | 11920 | 11920 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 238400 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 9.2 | Feasibility Study | City of Hawthorne PSRE for Signal and associated improvements on Prairie Ave from 118th St. to Marine Ave. | 32643 | 32643 | 32643 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 652860 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBPH TO 2014-5 | Feasibility Study | City of Hermosa Beach PSR for Pacific Coast Highway (SR-1) / Aviation Blvd. Mobility Improvements Project | 190000 | 190000 | 190000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3800000 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBPH TO 9.3 | Feasibility Study | City of Inglewood PSRE for geometric improvements on La Cienega Blvd and Manchester Blvd. | 31664 | 31664 | 31664 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3166400 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 9.4 | Feasibility Study | City of Inglewood PSRE for Phase V of Inglewood's ITS Upgrades | 24434 | 24434 | 24434 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | - | Construction Cost Separate |  | 100% EA |  | 100%
Completed SBHP TO 2014-4 | Feasibility Study | City of Inglewood PSR for Manchester/La Cienega Bundled Projects: channelize and raise median Manchester Boulevard from Ash Avenue to La Cienega Boulevard, improve turn radii La Cienega Boulevard at Manchester Boulevard, improve turn radii and through-right lane La Cienega Boulevard at Florence Avenue | 23625 | 23625 | 23625 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2362500 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 2014-6 | Feasibility Study | City of Lawndale PSRE for Redondo Beach Blvd. Mobility Improvements from Prairie Ave. to Artesia Blvd. at I-405, from Hawthorne Bl. to Prairie Ave. Signal upgrades, concrete pads for transit, ADA ramps | 47360 | 47360 | 47360 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4736000 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 2014-7 | Feasibility Study | City of Manhattan Beach PSR for 7 intersections along Sepulveda Blvd (SR-1) corridor that were identified in the 2009 PCH Study conducted by SCAG and the SBCCOG: at Rosecrans., Marine Ave. / Cedar Ave., Valley Dr., 33rd St., 30th St., 14th St., and 2nd St. | 43043 | 43043 | 43043 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4304300 | Placeholder Est. |  | 100% EA |  | 100%
Completed Feas Study | Feasibility Study | Metro South Bay Baseline Arterial Performance Monitoring Implementation Study | 250000 | 250000 | 250000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 250000 | Complete |  | 100% EA |  | 100%
Completed SBHP TO 9.1 | Feasibility Study | City of Torrance PSRE for additional turn lanes on Western Ave. (SR-213) at Sepulveda Blvd. | 37921 | 37921 | 37921 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1896050 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 2014-2A | Feasibility Study | City of Torrance Western Ave (SR-213) at Sepulveda Blvd Intersection Improvements | 80000 | 80000 | 80000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4000000 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 2014-2B | Feasibility Study | City of Torrance PSR for Hawthorne Blvd. (SR-107) Corridor Improvements at Lomita Blvd, Emerald, Spencer, and 182nd Streets | 70000 | 70000 | 70000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3500000 | Placeholder Est. |  | 100% EA |  | 100%
COMPLETED PROJECTS
Completed MR312.22 D, C | Construction | City of El Segundo Maple Ave Arterial Improvements from Sepulveda Blvd to Parkview Ave | 2500000 | 2500000 | 2157575 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2157575 | Final Cost |  | 100% EA |  | 100%
Completed MR312.19 PD, D, C | Construction | City of Gardena Artesia Blvd at Western Ave Intersection Improvements (WB Left Turn Lanes) | 600000 | 600000 | 431825 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 431825 | Final Cost |  | 100% EA |  | 100%
Completed MR312.21 |  | City of Gardena Vermont Arterial Improvement From Rosecrans Ave to 182nd Street | 2350000 | 2350000 | 2350000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2350000 | Final Cost |  | 100% EA |  | 100%
Completed MR312.03 | Construction | City of Hawthorne Rosecrans Ave Arterial Improvements from I-405 SB Off-Ramp to Isis Ave | 2100000 | 2100000 | 2100000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2100000 | Final Cost |  | 100% EA |  | 100%
Completed MR312.44 |  | City of Hawthorne Hawthorne Blvd From El Segundo Blvd. to Rosecrans Ave | 7551000 | 7551000 | 7551000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 7551000 | Final Cost |  | 100% EA |  | 100%
Completed MR312.13 | Construction | City of Redondo Beach Aviation Blvd at Artesia Blvd Intersection Imp. | 22000 | 22000 | 19281.04 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 19281.04 | Final Cost |  | 100% EA |  | 100%
Completed MR312.14 | Construction | City of Redondo Beach Inglewood Ave at Manhattan Beach Blvd Intersection Improvements | 30000 | 30000 | 27122 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 27122 | Final Cost |  | 100% EA |  | 100%
Completed MR312.18 | Construction | City of Torrance Maple Ave at Sepulveda Blvd. Intersection Improvements | 540000 | 540000 | 319870.46 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 319870.46 | Final Cost |  | 100% EA |  | 100%
|  | TOTALS | 253522342.09 | 228177008.29 | 80621267.59 | 17157369.2356 | 11569152.7101 | 15455452.7804 | 18933934.2188 | 63115908.9449 | 10099914.4331 | 7398834.0053 | 7383783.2894 | 7055949.956 | 32528005.6838 | 3516628.5895 | 2017408 | 3877430.2222 | 4897630.2222 | 14826855.0339 | 3810522.2222 | 1826500 | 572500 | 2422500 | 9608263.2222 | 3201250 | 3221250 | 3241250 | 3241250 | 13859978 | 3125250 | 3145250 | 3144250 | 3144931 | 13613658 | 519994420.59
|  | FY 11 - FY 17 Request | 63115908.9449
|  | FY 11 - FY 17 Total (to date requests) | 143737176.5349
|  | FY 11 - FY 22 total (estimate to 2022) | 228173936.4748

## 2 SBHP Master
SBHP Measure R Project Expenditure Plan Cost & Cash Flow Budget
|  | Updated: 10/20/15 |  |  |  | 2016-2017 (FY 17) |  |  |  |  | 2017-2018 (FY 18) |  |  |  | Future Years | 2018-2019 (FY 19) |  |  |  |  | 2019-2020 (FY 20) |  |  |  |  | 2020-2021 (FY 21) |  |  |  |  | 2021-2022 (FY 22) |  |  |  |  | Total Project Est. Cost |  | Eligibility and Matching Policy
Metro Project ID FA Type | Phase | Lead Agency / Description | Phase Cost | Measure R Share FY11-22 | Est. Reimburse. by 6/30/16 | Q1 16-17 July-Sept | Q2 16-17 Oct-Dec | Q3 16-17 Jan-March | Q4 16-17 April-June | 16-17 TOTAL | Q1 17-18 July-Sept | Q2 17-18 Oct-Dec | Q3 17-18 Jan-March | Q4 17-18 April-June | 17-18 TOTAL | Q1 18-19 July-Sept | Q2 18-19 Oct-Dec | Q3 18-19 Jan-March | Q4 18-19 April-June | 18-19 TOTAL | Q1 19-20 July-Sept | Q2 19-20 Oct-Dec | Q3 19-20 Jan-March | Q4 19-20 April-June | 19-20 TOTAL | Q1 20-21 July-Sept | Q2 20-21 Oct-Dec | Q3 20-21 Jan-March | Q4 20-21 April-June | 20-21 TOTAL | Q1 21-22 July-Sept | Q2 21-22 Oct-Dec | Q3 21-22 Jan-March | Q4 21-22 April-June | 21-22 TOTAL | Total Project Est. Cost (All Phases and Sources) | Total Cost Est. Source | Eligibility | Measure R Percent | Measure R Revised by Lead Agency? | MBR Measure R Share
ADMINISTRATIVE
Administration & Miscellaneous Expense |  |  | 1022958.68 | 1022958.68 | 840930.68 | 7035 | 7035 | 7035 | 7035 | 28140 | 7247 | 7247 | 7247 | 7247 | 28988 | 7463 | 7463 | 7463 | 7463 | 29852 | 7688 | 7688 | 7688 | 7688 | 30752 | 7918 | 7918 | 7918 | 7918 | 31672 | 8156 | 8156 | 8156 | 8156 | 32624 |  |  |  | 100% |  | 100%
Program Development and Misc. Expenses (development, oversight, and intergovernmental relations) |  |  | 5696599.02 | 5696599.02 | 2439624.02 | 129595 | 129596 | 129597 | 129597 | 518385 | 140134 | 140134 | 140134 | 140134 | 560536 | 121975 | 121977 | 121977 | 121977 | 487906 | 136371 | 136372 | 136373 | 136373 | 545489 | 130825 | 130827 | 130827 | 130827 | 523306 | 155337 | 155338 | 155339 | 155339 | 621353 | 17577216.09 | All Admin |  | 100% |  | 100%
Feasibility Studies (previous reimbursement) |  |  | 1696661.39 | 1696661.39 | 496661.39 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 400000 |  |  |  |  | 400000 |  |  |  |  | 400000 | [5 empty] | 100%
ACTIVE FEASIBLITY/PLANNING STUDIES
EXECUTED MR312.57 PD | Feasibility Study | City of El Segundo Park Place from Nash St. to Allied Way, Roadway extension and railroad grade separation | 350000 | 350000 | 150000 |  | 150000 |  |  | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 35850000 | From Lead Agency |  | 50% | Future Funding Mix Not Identified | 100%
EXECUTED FEAS STUDY SBHP TO 2015-1 | Feasibility Study | Port of LA Vincent Thomas Bridge (SR-47) I-110 Connector | 1000000 | 1000000 | 112000 | 290000 | 314000 | 234000 | 50000 | 888000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1000000 | Construction Separate |  | 100% EA |  | 100%
EXECUTED MR312.24 | PA/ED | Caltrans PAED I-110 Auxiliary lane from SR-91 to Torrance Blvd Auxiliary lane & 405/110 Connector | 1500000 | 1500000 | 1500000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 30000000 | Placeholder Est. |  | 50% | Future Funding Mix Not Identified | 100%
EXECUTED MR312.25 | PA/ED | Caltrans PAED I-405 at 182nd St./Crenshaw Boulevard | 1700000 | 1700000 | 1700000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 34000000 | Placeholder Est. |  | 50% | Future Funding Mix Not Identified | 100%
EXECUTED MR312.56 | PA/ED | City of Los Angeles Review of Feas. Study on Del Amo Blvd from Western Ave to Vermont Ave. | 100000 | 100000 | 3277 | 24180.75 | 24180.75 | 24180.75 | 24180.75 | 96723 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3000000 | Placeholder Est. |  | 80% | Future Funding Mix Not Identified | 100%
EXECUTED MR312.16 | PA/ED | Los Angeles County Del Amo Boulevard from Normandie Boulevard to Vermont Ave | 1900000 | 1900000 | 1900000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 26000000 | Placeholder Est. |  | 50% | Future Funding Mix Not Identified | 100%
COMMITTED FEASIBLITY/PLANNING STUDIES
COMMITTED MR312.30 | Feasibility Study | Caltrans I-405 from I-110 to I-105 and I-105 from I-405 to Crenshaw: Corridor Refinement Studies | 700000 | 700000 |  | 75000 | 75000 | 75000 | 75000 | 300000 | 100000 | 100000 | 100000 | 100000 | 400000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 14000000 | Placeholder Est. |  | 100% EA | Future Funding Mix Not Identified | 100%
COMMITTED MR312.45 | PA/ED | Caltrans PAED/Implement an Integrated Corridor Management System along the SR -110 Corridor between Artesia Boulevard and the I-405. The project will integrate freeway, arterial and transit operations, implement a Decision Support System for coordinated agency operations and traveler information systems. | 1000000 | 1000000 | [5 empty] | 0 |  |  |  |  | 0 | 125000 | 125000 | 125000 | 125000 | 500000 | 125000 | 125000 | 125000 | 125000 | 500000 |  |  |  |  | 0 |  |  |  |  | 0 | 20000000 | Placeholder Est. |  | 100% EA | Future Funding Mix Not Identified | 100%
COMMITTED SBHP TO 2014-1 | Feasibility Study | City of El Segundo Aviation Blvd, Douglas St. and El Segundo Blvd. Commuter Bikeways Study | 150000 | 150000 |  |  | 150000 |  |  | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3000000 | Placeholder Est. |  | 100% EA | Future Funding Mix Not Identified | 100%
COMMITTED FEAS STUDY SBHP TO #-# | Feasibility Study | City of Torrance Pacific Coast Highway (SR-1) / Hawthorne Blvd. (SR-107) Park & Ride Feasibility Study | 150000 | 150000 | [5 empty] | 0 | 150000 |  |  |  | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3000000 | Placeholder Est. |  | 100% EA | Future Funding Mix Not Identified | 100%
COMMITTED FEAS STUDY SBHP TO #-# | Feasibility Study | City of Torrance 182nd St from Kingsdale Ave to Harbor Gateway Transit Center (e/o Vermont Ave.): feasibility of study various corridor improvements (intersection improvements, ITS, bicycle facilities, etc.). | 300000 | 300000 |  |  |  | 300000 |  | 300000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 6000000 | Placeholder Est. |  | 100% EA | Future Funding Mix Not Identified | 100%
NEW REQUEST FOR FEASIBILITY/PLANNING STUDIES
Requested | Feasibility Study | Caltrans I-405 from I-110 to I-105 (including a mile on either side of the freeway): Identify and prioritize operational improvements (aux. lanes, interchange configuration) to reduce travel delay. | 700000 | 700000 |  | 50000 | 50000 | 75000 | 75000 | 250000 | 75000 | 75000 | 75000 | 75000 | 300000 | 75000 | 75000 |  |  | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 14000000 | Placeholder Est. | Eligible | 100% |  | 100%
Requested | PSR | Caltrans SR-1 from eastern boundary of Carson to eastern boundary of Torrance - PSR | 170000 | 170000 |  |  |  | 85000 | 85000 | 170000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3400000 | Placeholder Est. | Eligible | 100% |  | 100%
Requested | PSR | Caltrans Western Ave.(SR-213) from Palos Verdes Drive North to northern boundary of Gardena - PSR | 170000 | 170000 |  |  |  | 85000 | 85000 | 170000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3400000 | Placeholder Est. | Eligible | 100% |  | 100%
Requested | Feasibility Study | City of Carson Avalon Boulevard Bridge over the Dominguez Channel: Investigate feasibility of an additional lane on the west side for a bike lane and widening of the east side sidewalk to improve flow in a constrained location. | 60000 | 60000 | [5 empty] | 0 | 60000 |  |  |  | 60000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 5000000 | Placeholder Est. | Eligible | 100% |  | 100%
Requested | PA/ED | City of El Segundo PA/ED Park Place from Nash St to Allied Way- Roadway extension and railroad grade separation, including utility and railroad relocation and construction. | TBD | TBD |  |  |  | 1000000 |  | 1000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | - | Design/Const Separate | Eligible - Nexus Project |  |  | 100%
Requested | PA/ED + Est Const./ ROW funding | City of Hermosa Beach PA/ED Aviation Bl from PCH to Prospect Ave - Arterial Improvements. | $1,800,000 PA/ED, $42m Cost/ROW | 22300000 |  |  |  | 1800000 |  | 1800000 |  |  |  |  | 0 | 273000 | 273000 | 894000 | 894000 | 2334000 | 894000 | 894000 |  | 1820000 | 3608000 | 1820000 | 1820000 | 1820000 | 1820000 | 7280000 | 1820000 | 1820000 | 1819000 | 1819000 | 7278000 | 44599000 | From Lead Agency | Eligible with Nexus Project elements | 100% | Yes | 50%
Requested | PA/ED | City of Inglewood PA/ED for Florence Ave at La Brea Ave - Construct new Downtown Inglewood Transit Center at La Brea Station of Crenshaw Line | 1500000 | 1500000 |  | 30000 | 30000 | 30000 | 30000 | 120000 | 30000 | 213750 | 213750 | 213750 | 671250 | 213750 | 213750 | 213750 | 67500 | 708750 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1500000 | Total Cost | Eligible, bus turnouts and demand reduction | 100% |  | 100%
Requested | PA/ED | Port of LA PA/ED for SR-47/Vincent Thomas Bridge and Front St/Harbor Bl Interchange Reconfiguration. | 12078500 | 12078500 | [5 empty] | 0 | 88125 | 88125 | 88125 | 88125 | 352500 | 187500 | 187500 | 187500 | 187500 | 750000 | 187500 | 187500 | 187500 | 187500 | 750000 | 1281250 | 1281250 | 1281250 | 1281250 | 5125000 | 1275250 | 1275250 | 1275250 | 1275250 | 5101000 | 23452000 | From Lead Agency | Eligible | 50% | Yes | 51.5%
Requested | Feasibility Study | City of Rancho Palos Verdes Western Ave (SR-213) from Palos Verdes Drive North to 25th St,: Feasibility study for improvements in coordination with Lomita, LADOT, and Caltrans. | 90000 | 90000 |  | 25000 | 15000 | 30000 | 20000 | 90000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1800000 | Placeholder Est. | Eligible | 100% |  | 100%
ACTIVE PROJECTS
EXECUTED MR312.11 | Design/ Construction | Caltrans ITS: I-405, I-110, I-105, SR-91 at freeways ramp/arterial signalized intersections - DCCM | 5000000 | 5000000 | 5000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 25000000 | Placeholder Est. |  | 100% EA |  | 100%
EXECUTED MR312.29 | Design/ Construction | Caltrans Pacific Coast Highway (SR-1) ITS with parallel arterials from I-105 to I-110 | 9000000 | 9000000 | 5472000 | 1250000 | 850000 | 728000 | 700000 | 3528000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 9000000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.37 | Design/ Construction | City of Carson Sepulveda Boulevard widening from Alameda Street to ICTF Driveway | 1158000 | 1158000 | 1158000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1158000 | Total Cost |  | 100% |  | 100%
EXECUTED MR312.17 | Design/ Construction | City of Gardena Rosecrans Ave Arterial Improvements From Vermont Ave to Crenshaw Blvd. | 5140000 | 5140000 | 1907759 | 808060.25 | 808060.25 | 808060.25 | 808060.25 | 3232241 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 5140000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.33 | Design/ Construction | City of Hawthorne Aviation Bl at Marine Ave; construct westbound right-turn lane. | 3600000 | 3600000 | 155000 | 145000 | 125000 | 25000 | 50000 | 345000 | 15000 | 30000 | 25000 | 230000 | 300000 |  |  | 300000 | 1500000 | 1800000 | 1000000 |  |  |  | 1000000 |  |  |  |  | 0 |  |  |  |  | 0 | 3600000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.05 | Design/ Construction | City of Hermosa Beach Pacific Coast Highway (SR-1) between Anita St and Artesia Blvd: Improvements | 304000 | 304000 | 202936 | 101063 |  |  |  | 101063 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 304000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.12 | Design/ Construction | City of Inglewood Citywide ITS Phase IV | 3500000 | 3500000 | 3500000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3500000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.15 | Design/ Construction | City of Lawndale Inglewood Ave From 156th st to I-405 SB On Ramp Improvements | 500000 | 500000 | 500000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 500000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.36 | Construction | City of Lawndale Traffic Signal Improvements Citywide | 1500000 | 1500000 | 1500000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1500000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.43 | Design/ Construction | City of Lomita Intersection Improvements at Western (SR-213) /Palos Verdes Dr. & Pacific Coast Highway (SR-1)/Walnut | 900000 | 900000 | 800000 | 100000 |  |  |  | 100000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 900000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.28 | Construction | City of Manhattan Beach Seismic retrofit of Sepulveda Blvd (SR-1) bridge 53-62 | 9100000 | 9100000 | 6461664 | 1319168 | 1319168 |  |  | 2638336 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 9100000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.04 | Construction | City of Manhattan Beach Sepulveda Blvd at Marine Ave (WB Left Turn Lane) | 365000 | 365000 | 364500 | 500 |  |  |  | 500 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 365000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.06 | Design/ Construction | City of Redondo Beach Pacific Coast Highway (SR-1) Arterial Improvements from Anita St to Palos Verdes Blvd | 1400000 | 1400000 | 150000 | 75000 | 115000 | 30000 | 280000 | 500000 | 250000 | 250000 | 250000 |  | 750000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1400000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.07 | Construction | City of Redondo Beach Pacific Coast Highway (SR-1) at Torrance Blvd Intersection Improvements | 585000 | 585000 | 127000 | 10000 | 148000 | 150000 | 150000 | 458000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 585000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.08 | Design/ Construction | City of Redondo Beach Pacific Coast Highway (SR-1) at Palos Verdes Blvd Intersection Improvements | 320000 | 320000 | 320000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 320000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.20 | Design/ Construction | City of Redondo Beach Aviation Blvd at Artesia Blvd Intersection Improvements | 847000 | 847000 | 350000 | 165000 | 172000 | 160000 |  | 497000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 847000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.42 | Design/ Construction | City of Redondo Beach Inglewood Ave at Manhattan Beach Bl: Add SB right-turn lane south of railroad tracks to Manhattan Beach Bl | 5175000 | 5175000 | 117000 | 70000 | 68000 | 733000 | 782000 | 1653000 | 730000 | 730000 | 40000 | 40000 | 1540000 | 10000 | 365000 | 375000 | 375000 | 1125000 | 370000 | 370000 |  |  | 740000 |  |  |  |  | 0 |  |  |  |  | 0 | 5175000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.10 | Design/ Construction | City of Torrance Pacific Coast Highway (SR-1) at Hawthorne Blvd (SR-107) Intersection Improvements | 19600000 | 19600000 | 9600000 | 500000 | 500000 | 500000 | 8500000 | 10000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 19600000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.23 | Design/ Construction | City of Torrance Torrance Park and Ride Regional Terminal | 18100000 | 18100000 | 10000000 | 3000000 | 3000000 | 2100000 |  | 8100000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 18100000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.26 | Design/ Construction | City of Torrance I-405 at 182nd St. /Crenshaw Blvd. operational improvements | 15300000 | 15300000 | 5300000 | 5000000 |  |  |  | 5000000 | 5000000 |  |  |  | 5000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 15300000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.40 | Design/ Construction | City of Torrance Pacific Coast Highway (SR-1) at Vista Montana/Anza Ave Intersection Improvement | 2900000 | 2900000 | 900000 | 500000 | 500000 | 500000 | 500000 | 2000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2900000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.58 | Design/ Construction | City of Torrance Pacific Coast Highway (SR-1) from Calle Mayor to Janet Ln. safety improvement. | 852000 | 852000 | 200000 | 200000 | 200000 | 252000 |  | 652000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 852000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.59 | Design/ Construction | City of Torrance PCH at Madison Ave- Signal Upgrades to provide left-turn phasing | 500000 | 500000 | 100000 | 400000 |  |  |  | 400000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 500000 | Total Cost |  | 100% EA |  | 100%
EXECUTED MR312.60 | Design/ Construction | City of Torrance Crenshaw Blvd. from Del Amo to Dominguez; three Southbound turn lanes at 1) Del Amo Blvd; 2) extension of 208th St; 3) Transit Center Entrance. Signal Improvements at two existing and new signal at Transit Center and extension of 208th St. | 3300000 | 3300000 | 1300000 | 1000000 | 1000000 |  |  | 2000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3300000 | Total Cost |  | 100% EA |  | 100%
COMMITTED PROJECTS
COMMITTED MR312.47 | Construction | City of Hawthorne Prairie Ave from 118th St to Marine Ave- Signal Improvements | 1237000 | 1237000 |  |  |  |  | 204114 | 204114 | 204114 | 204114 | 204114 | 204114 | 816456 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1237000 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.50 | Construction | City of Inglewood Citywide ITS Phase V- Communication gap closure on various locations, TS upgrade and arterial detection | 384000 | 384000 | [5 empty] | 0 | 14000 | 14000 | 14000 | 109000 | 151000 | 58250 | 58250 | 58250 | 58250 | 233000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 384000 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.53 | Construction | City of Lawndale Redondo Beach Blvd. Mobility Improvements from Prairie to Artesia (PSRE) at I-405, from Hawthorne Bl. to Prairie Ave- PS&E / ROW Acquisition; Signal upgrades, concrete pads for transit, ADA ramps | 1039262 | 1039262 | [5 empty] | 0 | 129908 | 129908 | 129908 | 129908 | 519632 | 129908 | 129908 | 129908 | 129908 | 519632 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1039262 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.51 | Construction | City of Los Angeles Anaheim St from Farragut Ave to Dominguez Channel- Widen from 78' to 84' and restripe to accommodate an additional lane in each direction | 3141450 | 3141450 |  | 150000 | 150000 | 150000 | 150000 | 600000 | 150000 | 150000 | 150000 | 150000 | 600000 | 500000 | 500000 | 500000 | 441450 | 1941450 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3141450 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.52 | Construction | Los Angeles County 2013 CFP South Bay Forum systemwide operational improvements, coordination and timing, and ITS improvements | 1021000 | 1021000 | [5 empty] | 0 |  |  |  |  | 0 | 10000 | 15000 | 25000 | 50000 | 100000 | 40000 | 50000 | 60000 | 90000 | 240000 | 100000 | 120000 | 140000 | 140000 | 500000 | 30000 | 50000 | 50000 | 50681 | 180681 | 1021000 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.34 | Construction | City of Manhattan Beach Construct SB and WB right-turn lanes on Aviation at Artersia. The project will include right-of-way acquisition, utility relocation, street widening and restriping of the northwest corner of the Aviation Blvd. and Artesia Blvd. intersection. | 1500000 | 1500000 | 151000 | 369000 | 78000 | 602000 | 300000 | 1349000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1500000 | Total Cost |  | 100% EA |  | 100%
COMMITTED MR312.35 | Construction | City of Manhattan Beach Sepulveda Blvd (SR-1) at Manhattan Beach Blvd Intersection Improvement. Add left-turn lanes. The project will include right-of-way acquisition, utility relocation, street widening and restriping of the intersection. | 980000 | 980000 |  | 11000 | 54800 | 34000 | 50000 | 149800 | 50000 | 48000 | 244000 | 244000 | 586000 | 244200 |  |  |  | 244200 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 980000 | Total Cost |  | 100% EA |  | 100%
COMMITTED PROJECT MR312.09 | PD/EA and PS&E | City of Torrance Pacific Coast Highway (SR-1) and Crenshaw Ave- Preliminary Design, EIR and P.S.&E. for operational improvements | 1300000 | 1300000 |  |  |  |  | 1300000 | 1300000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 6500000 | Placeholder Est. |  | 100% EA |  | 100%
COMMITTED MRE312.# | PS&E | City of Torrance Hawthorne Bl (SR-107) at: 182nd Street, Spencer Street, Emerald Street, and Lomita Blvd. P.S.&E for roadway widening to construct new northbound right turn lanes | 810000 | 810000 | [5 empty] | 0 | 810000 |  |  |  | 810000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | - | Construction Cost Est. Separate |  | 100% EA |  | 100%
NEW REQUEST FOR PROJECTS
Requested | Design/ Construction | City of Carson Widen Sepulveda Blvd for 1,475 linear feet to provide three lanes of traffic in both directions and a raised median, the project involves widening the bridge over the Dominguez Channel. | 6375903 | 5500722.4 |  | 687590.4078 | 491135.8824 | 2750361.6314 | 1571635.3412 | 5500723.2627 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 6375903 | Total Cost | Eligible - Nexus Project | 80% | No | 86.27%
Requested | Design/ Construction | City of Carson Victoria St at Tamcliff Ave - Installation of left-turn phases. | 120000 | 120000 |  | 30000 | 30000 | 30000 | 30000 | 120000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 120000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Carson 223rd St from Lucerne Ave to Alameda St.: widening roadway and install median. | 3601766 | 3281412.8 |  | 410176.8278 | 410176.8278 | 410176.8278 | 410176.8278 | 1640707.3111 | 410176.8278 | 410176.8278 | 410176.8278 | 410176.8278 | 1640707.3111 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3601766 | Total Cost | Eligible, enhancement portion is $100k (3%) | 80% | No | 91.11%
Requested | Design/ Construction | City of Carson Figueroa St. at 234th St. - Upgrade the traffic signal equipment to modernize the controller and signal lights | 150000 | 150000 |  | 37500 | 37500 | 37500 | 37500 | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 150000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested |  | City of Carson Traffic Signal Upgrade at Intersection of 213th Street and Dolores Street | 150000 | 150000 | [5 empty] | 0 |  |  |  |  | 0 | 37500 | 37500 | 37500 | 37500 | 150000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 150000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Carson Traffic Signal upgrades at 10 intersections: Figueroa St. at Victoria St., Main St. at 220th St., Main St. at Victoria St., Main St. at Albertoni St., Figueroa St. at 223rd St., Broadway at Victoria St., Albertoni St., Gardena Blvd., Alondra Blvd. and a midblock crossing south of Albertoni Blvd. | 1400000 | 1400000 |  | 187500 | 37500 | 37500 | 37500 | 300000 | 37500 | 37500 | 37500 | 37500 | 150000 | 37500 | 37500 | 37500 | 37500 | 150000 | 200000 | 200000 | 200000 | 200000 | 800000 |  |  |  |  | 0 |  |  |  |  | 0 | 1400000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Gardena Crenshaw Bl from El Segundo Bl to Redondo Beach Bl - Arterial Improvements, traffic signal upgrades and synchronization, add turn pockets where feasible, traffic channelization. | 1900000 | 1900000 |  |  |  | 58000 | 58000 | 116000 | 57000 | 575000 | 576000 | 576000 | 1784000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1900000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Gardena Redondo Beach Bl from Crenshaw Bl to Vermont Ave - Arterial Improvements, traffic signal upgrades and synchronization, add turn pockets where feasible, traffic channelization. | 3600000 | 3280000 |  |  |  |  | 25511.1111 | 25511.1111 | 24600 | 61955.5556 | 61955.5556 | 61955.5556 | 210466.6667 | 61955.5556 |  | 994022.2222 | 994022.2222 | 2050000 | 994022.2222 |  |  |  | 994022.2222 |  |  |  |  | 0 |  |  |  |  | 0 | 3600000 | Total Cost | Eligible - Nexus Project | 80% | No | 91.11%
Requested | Design/ Construction | City of Gardena Normandie Ave from El Segundo Bl to 177th St - Arterial Improvements, traffic signal upgrades and synchronization, add turn pockets where feasible, traffic channelization, transit access. | 4000000 | 3600000 |  |  |  | 108900 | 108900 | 217800 | 108900 | 818100 | 819000 | 818100 | 2564100 | 818100 |  |  |  | 818100 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4000000 | Total Cost | Eligible - Nexus Project | 80% | No | 90%
Requested | Design/ Construction | City of Gardena Van Ness Ave from El Segundo Bl to Redondo Beach Bl - Arterial Improvements, traffic signal upgrades and synchronization, add turn pockets where feasible, traffic channelization. | 3000000 | 2800000 |  |  |  | 124133.3333 | 130666.6667 | 254800 | 636533.3333 | 636533.3333 | 636533.3333 | 635600 | 2545200 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3000000 | Total Cost | Eligible - Nexus Project | 80% | No | 93.33%
Requested | Design/ Construction | City of Gardena Artesia Bl from Western Ave to Vermont Ave - Arterial Improvements, traffic signal upgrades and synchronization, add turn pockets, traffic channelization. | 2654000 | 2523200 |  |  |  | 77007.9879 | 76057.272 | 153065.26 | 76057.272 | 758671.2886 | 757720.5727 | 757720.5727 | 2350169.7061 | 19965.0339 |  |  |  | 19965.0339 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2654000 | Total Cost | Eligible - Nexus Project | 80% | No | 95.07%
Requested | Design/ Construction | City of Gardena Rosecrans Ave at Vermont Ave & Redondo Beach Bl at Vermont Ave - Traffic Signal upgrades and synchronization, add turn pockets, traffic channelization. | 1500000 | 1500000 |  |  |  | 20000 | 38000 | 58000 | 38000 | 38000 | 456000 | 455000 | 987000 | 455000 |  |  |  | 455000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1500000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Hawthorne Inglewood Ave at El Segundo Bl, Crenshaw Bl at Rocket Road & Crenshaw Bl at Jack Northrop - Intersection widening improvements & traffic signal modifications | 2000000 | 2000000 |  |  | 500000 | 600000 | 900000 | 2000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2000000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
Requested | Design/ Construction | City of Hawthorne Hawthorne Bl from 120th St to 111th St - Arterial Improvements | 5000000 | 4400000 |  |  |  | 400000 | 700000 | 1100000 | 500000 | 1000000 | 800000 | 1000000 | 3300000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 5000000 | Total Cost | Eligible - Nexus Project | 80% | Yes | 88%
Requested | Design/ Construction | City of Hawthorne El Segundo Blvd. from Hawthorne Blvd. to Crenshaw Bl - Upgrade signals, improve right and left-turn lanes | 3000000 | 2800000 |  |  |  | 100000 | 400000 | 500000 | 300000 | 1000000 | 1000000 |  | 2300000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3000000 | Total Cost | Eligible - Nexus Project | 80% | Yes | 93.33%
Requested | Design/ Construction | City of Manhattan Beach Sepulveda Bl at Rosecrans Ave, 33rd St, Cedar Ave, 14th St & 2nd St - Operational Improvements. | 900000 | 900000 |  |  | 30000 | 30000 | 30000 | 90000 | 5000 | 5000 | 270000 | 270000 | 550000 | 260000 |  |  |  | 260000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 900000 | Total Cost | Eligible | 100% | Yes | 100%
Requested | Design/ Construction | Los Angeles County Wilmington Ave north of Del Amo Blvd.: Construct safety improvements at railroad crossing | 600000 | 600000 |  |  |  | 25000 | 25000 | 50000 | 50000 | 25000 | 25000 | 450000 | 550000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 600000 | Total Cost | Eligible - Nexus Project | 100% | Yes | 100%
COMPLETED FEASIBILITY/PLANNING STUDIES
Completed TO 2014-3 A-F | Feasibility Study | City of Gardena Feasibility Studies for 2015 Metro CFP | 42632 | 42632 | 42632 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 852640 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 9.5 | Feasibility Study | City of Gardena PSRE for three park and ride facilities | 11920 | 11920 | 11920 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 238400 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 9.2 | Feasibility Study | City of Hawthorne PSRE for Signal and associated improvements on Prairie Ave from 118th St. to Marine Ave. | 32643 | 32643 | 32643 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 652860 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBPH TO 2014-5 | Feasibility Study | City of Hermosa Beach PSR for Pacific Coast Highway (SR-1) / Aviation Blvd. Mobility Improvements Project | 190000 | 190000 | 190000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3800000 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBPH TO 9.3 | Feasibility Study | City of Inglewood PSRE for geometric improvements on La Cienega Blvd and Manchester Blvd. | 31664 | 31664 | 31664 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3166400 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 9.4 | Feasibility Study | City of Inglewood PSRE for Phase V of Inglewood's ITS Upgrades | 24434 | 24434 | 24434 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | - | Construction Cost Separate |  | 100% EA |  | 100%
Completed SBHP TO 2014-4 | Feasibility Study | City of Inglewood PSR for Manchester/La Cienega Bundled Projects: channelize and raise median Manchester Boulevard from Ash Avenue to La Cienega Boulevard, improve turn radii La Cienega Boulevard at Manchester Boulevard, improve turn radii and through-right lane La Cienega Boulevard at Florence Avenue | 23625 | 23625 | 23625 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2362500 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 2014-6 | Feasibility Study | City of Lawndale PSRE for Redondo Beach Blvd. Mobility Improvements from Prairie Ave. to Artesia Blvd. at I-405, from Hawthorne Bl. to Prairie Ave. Signal upgrades, concrete pads for transit, ADA ramps | 47360 | 47360 | 47360 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4736000 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 2014-7 | Feasibility Study | City of Manhattan Beach PSR for 7 intersections along Sepulveda Blvd (SR-1) corridor that were identified in the 2009 PCH Study conducted by SCAG and the SBCCOG: at Rosecrans., Marine Ave. / Cedar Ave., Valley Dr., 33rd St., 30th St., 14th St., and 2nd St. | 43043 | 43043 | 43043 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4304300 | Placeholder Est. |  | 100% EA |  | 100%
Completed Feas Study | Feasibility Study | Metro South Bay Baseline Arterial Performance Monitoring Implementation Study | 250000 | 250000 | 250000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 250000 | Complete |  | 100% EA |  | 100%
Completed SBHP TO 9.1 | Feasibility Study | City of Torrance PSRE for additional turn lanes on Western Ave. (SR-213) at Sepulveda Blvd. | 37921 | 37921 | 37921 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1896050 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 2014-2A | Feasibility Study | City of Torrance Western Ave (SR-213) at Sepulveda Blvd Intersection Improvements | 80000 | 80000 | 80000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4000000 | Placeholder Est. |  | 100% EA |  | 100%
Completed SBHP TO 2014-2B | Feasibility Study | City of Torrance PSR for Hawthorne Blvd. (SR-107) Corridor Improvements at Lomita Blvd, Emerald, Spencer, and 182nd Streets | 70000 | 70000 | 70000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 3500000 | Placeholder Est. |  | 100% EA |  | 100%
COMPLETED PROJECTS
Completed MR312.22 D, C | Construction | City of El Segundo Maple Ave Arterial Improvements from Sepulveda Blvd to Parkview Ave | 2500000 | 2500000 | 2157575 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2157575 | Final Cost |  | 100% EA |  | 100%
Completed MR312.19 PD, D, C | Construction | City of Gardena Artesia Blvd at Western Ave Intersection Improvements (WB Left Turn Lanes) | 600000 | 600000 | 431825 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 431825 | Final Cost |  | 100% EA |  | 100%
Completed MR312.21 |  | City of Gardena Vermont Arterial Improvement From Rosecrans Ave to 182nd Street | 2350000 | 2350000 | 2350000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2350000 | Final Cost |  | 100% EA |  | 100%
Completed MR312.03 | Construction | City of Hawthorne Rosecrans Ave Arterial Improvements from I-405 SB Off-Ramp to Isis Ave | 2100000 | 2100000 | 2100000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 2100000 | Final Cost |  | 100% EA |  | 100%
Completed MR312.44 |  | City of Hawthorne Hawthorne Blvd From El Segundo Blvd. to Rosecrans Ave | 7551000 | 7551000 | 7551000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 7551000 | Final Cost |  | 100% EA |  | 100%
Completed MR312.13 | Construction | City of Redondo Beach Aviation Blvd at Artesia Blvd Intersection Imp. | 22000 | 22000 | 19281.04 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 19281.04 | Final Cost |  | 100% EA |  | 100%
Completed MR312.14 | Construction | City of Redondo Beach Inglewood Ave at Manhattan Beach Blvd Intersection Improvements | 30000 | 30000 | 27122 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 27122 | Final Cost |  | 100% EA |  | 100%
Completed MR312.18 | Construction | City of Torrance Maple Ave at Sepulveda Blvd. Intersection Improvements | 540000 | 540000 | 319870.46 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 319870.46 | Final Cost |  | 100% EA |  | 100%
|  | TOTALS | 253522342.09 | 228177008.29 | 80621267.59 | 17157369.2356 | 11569152.7101 | 15455452.7804 | 18933934.2188 | 63115908.9449 | 10099914.4331 | 7398834.0053 | 7383783.2894 | 7055949.956 | 32528005.6838 | 3516628.5895 | 2017408 | 3877430.2222 | 4897630.2222 | 14826855.0339 | 3810522.2222 | 1826500 | 572500 | 2422500 | 9608263.2222 | 3201250 | 3221250 | 3241250 | 3241250 | 13859978 | 3125250 | 3145250 | 3144250 | 3144931 | 13613658 | 519994420.59
|  | FY 11 - FY 17 Request | 63115908.9449
|  | FY 11 - FY 17 Total (to date requests) | 143737176.5349
|  | FY 11 - FY 22 total (estimate to 2022) | 228173936.4748